UNEB  Project  Work

THEME:                Embracing Creativity and Practical Skills for Sustainable Development of Society

NAME:   JEREMIAH ROWLAND

CLASS:  Senior 3

STREAM: Violet

SUPERVISOR:  Teacher  N.Deborah

ASSISTANT SUPERVISOR:  Teacher Kalemera Isaiah

Title: An eco-friendly hydrogen extractor to solve Local Energy Society

Problem Statement:  High levels of local energy scarcity in Wakiso District hence leading to destruction of natural resources in the environment.

Purpose:   -  Producing clean energy at home from water hence providing clean fuel in the environment within two years.

OBJECTIVES:

Innovating and creating a low-cost Hydrogen generator for domestic use.

Energy from water in the environment within two years.

To increase on the energy resources the society.

To provide cleaner, cheaper and reliable energy in the society.

Justification:  The project is based on the available ways of reducing pollution hence making our societies safe and providing new energy resources so as to enhance man’s work.

RESOURCES:

Plastic  Bottles

Nails

Insulated wires

Project Activity Plan:

| Activities | Cost | Time frame | Person |
| --- | --- | --- | --- |
| Joining the plastic bottles | UGX 0 | 1 week | J. Rowland |
| Gathering nails | UGX 0 | 3 days | J. Rowland |
| Getting batteries and insulated wires | UGX 7000/= | 2 weeks | J. Rowland |
| Getting salt | UGX 0 | 1 week | J. Rowland |
| Assembling parts | UGX 0 | 1 month | J. Rowland |
| Final touches | UGX 0 | 1 month | J. Rowland |

Subjects:

Physics:             The electrical conductivity of the ions in the water enabling the production of hydrogen.

Technology and Design:  Designing physical appearance of the project.

Mathematics:  Measuring the proportions to be put in water so as to extract hydrogen.

Chemistry:       The chemical breakdown of hydrogen from water

English:  Typing and Printing the report.

Cross-cutting values

Environmental: Reduces accumulation of carbon in the environment through the provision of  clean energy hence enabling the growth of animals and other living organisms.

Health awareness: Reduces the risk of pollution in the environment through the production.

Socio-economic issues:  Promotes the sale of hydrogen in containers  cheaply better than natural gas hence promoting market for hydrogen later developing and out bringing peoples’ businesses through low prices attached to it than natural gas.

Citizenship and Patriotism:  Conserves environment since it is made of natural resource that do not pollute the environment.