MENGO SENIOR SCHOOL

PROJECT PROPOSAL

THEME:    EMBRACING CREATIVITY AND PRACTICAL SKILLS FOR SUSTAINABLE DEVELOPMENT OF SOCIETY

NAME: 		KATENDE JONATHAN FRED

CLASS:  		SENIOR THREE VIOLET

SCHOOL: 		MENGO SENIOR SCHOOL

INDEX NO.: 		73V/MB/23

YEAR:  		2026

Theme: Embracing Creativity and Skills for sustainable development of Society

Title: Making a solar food dryer to preserve fruits and vegetables in the society.

Purpose:   -The project is aimed at preserving fruits and vegetables in homesteads.

OBJECTIVES:   The project is aimed to:

To preserve fruits and vegetables in one to two days.

To reduce losses of fruits and vegetable by farmers in 2 weeks.

Justification:

The project will enable people in homes to preserve fruits and vegetables like onions for a longer time.

RESOURCES:

- Timber

- Wire mesh

- Nails

- Hammer

- Hacksaw

- Dear polythene

RESOURCE USE

Timber                      -- It is used for forming the frame of the solar food dryer.

Wire mesh               -- It is used as a base for putting fruits and vegetables.

Nails                          -- Used to join timber together.

Hammer                   -- Used for driving nails in he timber.

Clear polythene      -- It is used as cover at the top

Hacksaw                   -- It is used for cutting timber.

Project Activity Plan:

| Activities | Cost | Time frame | Person |
| --- | --- | --- | --- |
| Cutting timber into desired length using hack saw | UGX 7,000 | 1 -2 hours | Jonathan |
| Joining timber using nails and a hammer | UGX 2,000 | 1 hours | Jonathan |
| Putting the wire mesh onto the timber to form a base. | UGX 1,000 | 2 hours | Jonathan |
| Putting the polythene on the top of timber to form a clear hole. | UGX 1,000 | 2 hours | Jonathan |
| Making final touches | UGX 0(free) | 1 hour | Jonathan |

Subjects:

Agriculture               -- It’s involved in finding out ways of preserving fruits and vegetables.

Technology and design  --  It’s involved in the cutting and joining of timber

Mathematics   --  Measurement of appropriate  length of timber.

English              --  Writing the report and presentation

Cross-cutting values

Environmental:. It preserves food resources in community.

Mixed abilities: It mixes abilities like carpentry, elective one does i.e. Technology and design.

Abilities and involvement: The project develops various abilities including carpentry work, patience.

Socio-economic issues: The project involves preserving fruits and vegetables which promotes food security.